**Project Roadmap & Milestones**

|  |  |  |  |
| --- | --- | --- | --- |
| **Date/Time** | **Milestone** | **Task** | **Action Officer(s)** |
| **14 Jun 17** | Finalize Content | Framework | Charisse |
| Event Problem | Boyd, Joe, & Josh |
| Project Tools & Workspace | Boyd & Josh |
| **16 Jun 17** | Brief Key Stakeholders | SAF/A6/Cyber Patriot | Ken |
| AFITC/Legal | Josh |
| MACC/AU | Charisse |
| **20 Jun 17** | Registration Site Deployment | Tech MGM Portal | Charisse |
| Slack Workspace | Josh |
| MACC/Website | Boyd |
| **1 Jul 17** | Marketing Campaign Kickoff | Academia | Charisse |
| BES/26 NOS | Josh |
| HackMGM/Local Community | Josh & Boyd |
| SAF/A6 | Ken |
| Industry | Charisse, Joe, & Ken |
| **15 Jul –**  **24 Aug 17** | Participant Information Campaign Kickoff | Distribution of reading material, training, articles, etc. to spur ideas | Charisse, Josh, & Boyd |

**Schedule of Events**

|  |  |
| --- | --- |
| Date/Time | Event |
| 25 Aug 17 | Event Kickoff |
| 27 Aug 17 5PM | Event Social |
| 28 Aug 17 12PM | Completion Deadline |
| 28 Aug 17 5PM – 8PM | Presentation/Judging |
| 30 Aug 17 8AM | Winner Announcement & Presentation to AFITC Audience |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **August 2017** | | | | | | |
| ***Sunday*** | ***Monday*** | ***Tuesday*** | ***Wednesday*** | ***Thursday*** | ***Friday*** | ***Saturday*** |
| 20 | 21 | 22 | 23 | 24 | 25 | 26 |
|  |  |  |  |  | **@12AM**  Event Kickoff |  |
| 27 | 28 | 29 | 30 | 31 |  |  |
| **@5PM**  Event Social | AFITC | | |  |  |  |
| **@12PM**  Project Deadline  **@5PM**  Presentation & Judging |  | **@8AM**  Winner Announcement & AFITC Presentation |